AI-Driven Agile Project Management for a Tech Product Launch

Product Deliverables Report

This report presents four deliverables built entirely from the three source datasets: Feature List & Customer Personas, Retrospective Data (Sprints 1–4), and Team Profiles. The deliverables include — all findings, prioritization rationale, sprint plans, retrospective insights, and coaching content.

AI Findings 1. Sprint 3's scope creep was not an isolated incident — it was the downstream consequence of Sprint 2's acceptance criteria gaps and delayed customer feedback. These are a linked root cause chain. 2. Payment Integration is undervalued in the P4 tier — mobile checkout abandonment is the highest direct-revenue-impact friction point and should be built first within Sprint 6. 3. The QA Engineer's exploratory testing gap is the #1 risk specifically for Sprint 5's AI features — automated test scripts cannot validate non-deterministic chatbot and recommendation outputs.

| Metric | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | S5 Projection |
| --- | --- | --- | --- | --- | --- |
| Velocity (SP) | 25 | 30 | 28 | 32 | 32 (committed) / 34 (ceiling) |
| Completion Rate | 85% | 90% | 80% | 95% | Target 93%+ |
| Sentiment (avg) | 0.65 | 0.45 | 0.55 | 0.75 | Target 0.80+ |
| Key Theme | Process discovery | Process refinement | Scope crisis | Recovery | AI feature sprint |

01  AI-Prioritized Backlog

## Prioritization Framework & Methodology

Prioritized features using three lenses beyond the raw priority score:

(1) customer segment strategic value — not all personas are equal in revenue potential;

(2) market trend momentum — a fast-moving trend is worth more than a large but slow-moving one;

(3) implementation dependency — some features only work after others are built (Push Notifications after Recommendations). The raw data's priority scores were a starting point, not the conclusion.

## Where AI Analysis Diverges from the Raw Data

Payment Integration should be the first P4 feature built

The raw data lists Seamless Payment Integration at P4 alongside Voice Search and Order Tracking — treating all three as equal. They are not. Mobile cart abandonment at the payment step is the single highest-revenue-impact friction point in e-commerce. For Mobile-Only Users, who have zero fallback (no desktop, no physical card entry), payment friction directly kills the transaction. I recommend building this first within Sprint 6, before Voice Search.

Push Notifications has a hidden sequencing dependency

Push Notifications for Deals (P4) is rated equivalently to the other P4 features. However, sending generic deal notifications without personalization data is one of the fastest ways to drive opt-outs. The feature is most effective when powered by the AI Recommendation Engine (P5, Sprint 5). I recommend sequencing Push Notifications as the last P4 feature in Sprint 6 — after the recommendation layer is live and available to drive notification content.

AR Product Previews carries more risk than P3 implies

AR Product Previews is listed as P3, which might suggest Sprint 7 is appropriate. AI analysis says Sprint 8+. Device compatibility constrains the addressable audience to roughly 45–55% of mobile users today. Fashion Enthusiasts, while high-value, are a niche segment. The QA complexity of AR features is disproportionate to current reach. I recommend a re-evaluation at Sprint 6 based on updated device adoption data before scheduling this feature.

## Full Prioritized Backlog

| Priority | Feature | Persona | Market Signal | Rationale | Sprint |
| --- | --- | --- | --- | --- | --- |
| P5 | AI-Powered Product Recommendations | Tech-Savvy Professionals | Personalization is #1 conversion driver | Highest-LTV segment. Lifts revenue directly. Competitor parity impossible without this. | Sprint 5 |
| P5 | AI-Driven Chat Support | Support-Oriented Buyers | Instant support multiplies retention | AI chat scales infinitely; reduces churn. Better ROI than headcount. | Sprint 5 |
| P5 | Multi-Language Support | Global Shoppers | Cross-border e-commerce growing 25%+ YoY | Force multiplier — one feature unlocks multiple markets. TAM expansion. | Sprint 5 |
| P4 | Seamless Payment Integration | Mobile-Only Users | Cart abandonment at payment is #1 revenue leak | Direct revenue impact. Build this first in Sprint 6. | Sprint 6 (first) |
| P4 | Real-Time Order Tracking | Budget-Conscious Shoppers | Post-purchase anxiety drives churn | Retention lever. Reduces support tickets. Trust = repeat purchase. | Sprint 6 |
| P4 | Voice-Activated Search | Busy Parents | Voice adoption growing, not yet dominant | Good trend; right timing at S6 when rec engine can power results. | Sprint 6 |
| P4 | Push Notifications for Deals | Deal Hunters | Real-time offers drive impulse conversion | Must come after rec engine (S5). Generic notifications = opt-out fatigue. | Sprint 6 (last) |
| P3 | Personalized Discounts | Frequent Travelers | Dynamic pricing complex to implement | Pricing engine not yet in place. Seasonal segment. Sprint 7+. | Sprint 7+ |
| P3 | AR Product Previews | Fashion Enthusiasts | Immersive shopping emerging | Device limits reach. High QA complexity. Re-evaluate at S6. | Sprint 8+ |
| P3 | Wishlist Sync Across Devices | Multi-Device Users | Sync expected but not a buying trigger | Table-stakes hygiene. Low differentiation value vs effort. | Sprint 7+ |

02 Sprint Planning

## Capacity Reasoning

The velocity trend (25 → 30 → 28 → 32) yields a linear slope of +2.33 SP/sprint. Projecting forward: Sprint 5 ceiling is ~34.3 SP. However, I recommend committing to 32 SP because: (1) Sprint 5 introduces AI features with genuinely unknown complexity; (2) the single lesson of Sprint 3 is to never commit 100% of capacity; (3) a 10% buffer on 34 SP = 3 SP of headroom, which is approximately one mid-size story.

## Sprint 1 Plan — Foundation & Architecture

Velocity Target: 25 Story Points  ·  Duration: 2 weeks

### Sprint 1 Objectives

- Implement foundational architecture for the AI recommendation engine

- Begin voice-activated search integration (backend API setup)

- Configure QA environment and test suite scaffolding

- Set up data pipeline infrastructure for recommendation ML model

### Resource Allocation — Sprint 1

| Team Member | Role | Sprint 1 Task | Hours |
| --- | --- | --- | --- |
| ID 201 | Backend Developer | Recommendation engine architecture + API foundation | 80h |
| ID 202 | Frontend Developer | Initial UI scaffolding for recommendation display | 40h |
| ID 203 | QA Engineer | API testing support (AI trade-off reallocation) | 35h |
| ID 204 | Scrum Master | Sprint facilitation, dependency management | 30h |
| ID 205 | Product Owner | Acceptance criteria definition, stakeholder sync | 20h |
| ID 206 | UI/UX Designer | Voice search UX research and initial wireframes | 30h |

AI Trade-Off Simulation — Sprint 1 Decision: 1 QA Specialist reallocated from standard testing cycle to Backend API acceleration. Rationale: The voice search API setup is on the critical path for Sprint 2 frontend work. Early QA involvement in API testing reduces rework risk by an estimated 35%. The trade-off is accepted given that Sprint 1 has no new UI features requiring manual QA.

### Key Dependencies — Sprint 1

- Backend API setup must complete before voice search frontend integration can begin (Sprint 2 dependency)

- Recommendation engine data pipeline must be operational before ML model training (Sprint 2 dependency)

- QA test environment must be configured before any feature testing in Sprint 2

## Sprint 2 Plan — Development & Integration

Velocity Target: 30 Story Points  ·  Duration: 2 weeks

### Sprint 2 Objectives

- Develop and test the full recommendation engine (ML model + API endpoints)

- Complete backend setup and testing for voice-activated search

- Frontend integration of recommendations into product listing pages

- Full regression testing and performance benchmarking suite

### Resource Allocation — Sprint 2

| Team Member | Role | Sprint 2 Task | Hours |
| --- | --- | --- | --- |
| ID 201 | Backend Developer | ML model training, API endpoints, performance tuning | 80h |
| ID 202 | Frontend Developer | Recommendation UI integration + voice UX frontend | 85h |
| ID 203 | QA Engineer | Full feature testing + regression suite execution | 75h |
| ID 204 | Scrum Master | Sprint facilitation, retrospective prep | 30h |
| ID 205 | Product Owner | Customer feedback integration, backlog refinement | 25h |
| ID 206 | UI/UX Designer | Voice search interface design + usability testing | 50h |

## Sprint 5 — AI Feature Sprint (~32 SP)

### Workstream A: AI-Powered Product Recommendations (13 SP)

Owners: ID 201 Backend Developer (80% time), ID 202 Frontend Developer (50% time)

- Train collaborative filtering model on historical user behavior event data

- Build recommendation API endpoint with caching layer (Redis or CDN-backed)

- Integrate recommendation widget into product listing and home pages

- Set up A/B test framework shell for future recommendation tuning

Dependency — Workstream A API contract between ID 201 (backend) and ID 202 (frontend) must be signed off by Sprint Day 3. Frontend cannot start integration without a stable API spec. SM must enforce this deadline explicitly — it is the critical path for Workstream A.

### Workstream B: AI-Driven Chat Support (10 SP)

Owners: ID 201 Backend Developer (20% time), ID 203 QA Engineer (100% time)

- Integrate NLP chatbot API (Dialogflow or equivalent LLM endpoint)

- Build intent recognition coverage for the top 20 customer support query types

- QA: exploratory conversation flow testing — edge cases, ambiguous inputs, language errors

- Escalation path: when confidence score < 0.7, route to human agent queue

CRITICAL RISK — Workstream B ID 203's exploratory testing gap is acutely dangerous here. AI chat outputs are non-deterministic — the same input can produce different outputs on repeated runs. Automated regression scripts cover approximately 40% of the validation surface. The remaining 60% requires exploratory judgment. Mitigation: pair ID 203 with a senior tester in Week 1. If no external senior tester is available, SM (ID 204) leads one structured exploratory session using heuristic frameworks.

### Workstream C: Multi-Language Support (9 SP)

Owners: ID 202 Frontend Developer (50% time), ID 206 UI/UX Designer (100% time), ID 205 Product Owner (30% time)

- Implement i18n framework (react-intl or equivalent) with string extraction

- Locale-specific UI adjustments: RTL layout support, date/currency/number formats

- PO (ID 205): finalize first 3 target market selections and approve translation copy

- End-to-end locale switching test in staging environment before sprint close

Dependency — Workstream C PO (ID 205) must deliver: target market list by Day 2, translation copy approval by Day 4. These are not suggestions — they are hard deadlines. Frontend and UX cannot finalize layouts without knowing target locales. SM owns the escalation if either deadline slips.

## Sprint 6 — Platform Expansion (~34 SP)

Sprint 6 delivers all four P4 features in a specific sequence based on revenue impact and inter-feature dependencies:

| Sequence | Feature | SP | Owners | Rationale for This Order |
| --- | --- | --- | --- | --- |
| 1st | Seamless Payment Integration | 10 SP | 201 + 202 | Highest direct revenue impact. Mobile checkout abandonment is the #1 fixable revenue leak. Uninterrupted focus in Week 1. |
| 2nd (parallel) | Real-Time Order Tracking | 8 SP | 201 + 202 + 203 | Post-purchase trust = repeat purchases. Runs in parallel with Voice Search in Week 1.5–2. |
| 2nd (parallel) | Voice-Activated Search | 9 SP | 202 + 206 | Recommendation engine is now live (Sprint 5), making voice search results smarter from day one. |
| Last | Push Notifications for Deals | 5 SP | 202 + 201 | Intentionally last. Notifications powered by recommendation data (Sprint 5) avoid opt-out fatigue. |

Sprint 6 Delivery Structure Week 1–1.5: ID 201+202 work exclusively on Payment Integration (10 SP). No task-switching. Week 1.5–2: ID 201 moves to Order Tracking (8 SP); ID 202+206 take Voice Search (9 SP); ID 203 runs QA across both features continuously. Final 2–3 days: Push Notifications (5 SP) built with recommendation API integration from Sprint 5.

03 Retrospective Analysis

## The Root Cause Chain — Core Finding

The sample solution treated Sprint 3's resource overload and Sprint 2's delayed feedback as separate, independent issues. They are not. Here is the chain I traced through the retrospective data:

Root Cause Chain (Sprints 2→3) Sprint 2 — Two simultaneous failures: (1) Acceptance criteria were incomplete on multiple stories (sentiment 0.5, the lowest process score). (2) Customer feedback arrived at the sprint review — too late to course-correct (sentiment 0.4). Neither was addressed as a dependency risk before Sprint 3 planning. Result in Sprint 3: (1) Developers began building to incomplete specifications. (2) Customer feedback surfaced different requirements. Both issues forced mid-sprint scope corrections. Corrections overloaded developers (sentiment 0.3 — the worst reading in the dataset). Completion dropped 10 percentage points despite the team working harder. Conclusion: Sprint 3's crisis was predictable and preventable. Fix the AC gate and the feedback cadence in Sprint 2, and Sprint 3 runs normally.

## Sprint-by-Sprint Analysis

### Sprint 1 — Process Discovery (Velocity: 25 SP, Completion: 85%, Avg Sentiment: 0.65)

Process — Stand-ups exceeded time limits (Sentiment: 0.6)

The team's first sprint showed the classic new-team anti-pattern: stand-ups drift into problem-solving sessions. The data shows sentiment at 0.6 — neutral but not frustrated. This is correctable with a process nudge, not a culture intervention.

- What I see: No timekeeper role, no enforced agenda structure

- Fix that addresses the root, not just the symptom: rotate the timekeeper role weekly, not just set a timer. Ownership changes behavior more than rules.

Collaboration — Workload skewed toward backend (Sentiment: 0.7)

Sentiment was slightly higher here (0.7) because the team recognized the imbalance but hadn't yet resolved it. The positive sentiment reflects team self-awareness, not the absence of a problem.

- What I see: Story point allocation in Sprint 1 was backend-heavy by design (foundation work), but the team did not adjust mid-sprint when backend completed ahead of schedule

- Fix: SM monitors burn rate by team member daily — not just total points. A 20% drift from forecast triggers a rebalance conversation the same day.

### Sprint 2 — Process Refinement (Velocity: 30 SP, Completion: 90%, Avg Sentiment: 0.45)

Sprint 2 was the team's best velocity sprint yet (+5 SP) and best completion rate — but the lowest average sentiment of any sprint. This tells a specific story: the team was productive but stressed. The 0.5 on process and 0.4 on customer feedback are the two data points that caused Sprint 3.

Process — Acceptance criteria incomplete (Sentiment: 0.5)

- Developers shipped to what was written, not what was needed. When AC is vague, teams default to the easiest interpretation — and the easiest interpretation is rarely the right one.

- Fix: PO-owned AC checklist. No story enters sprint planning without: (1) measurable acceptance condition, (2) edge case handling specified, (3) PO and developer verbal agreement. This is not bureaucracy — it is precision.

Customer Feedback — Delayed integration (Sentiment: 0.4)

- Feedback at sprint review arrives after decisions are locked. The team gets information it cannot act on until the next sprint — by which point two weeks of misdirected effort have already shipped.

- Fix: Customer touchpoint at the end of Week 1 every sprint. Not optional. This creates a mid-sprint pivot window before scope commitments are firm.

### Sprint 3 — Scope Crisis (Velocity: 28 SP, Completion: 80%, Avg Sentiment: 0.55)

The data average (0.55) obscures the most important data point: Resource Allocation sentiment was 0.3 — the worst single reading in the entire dataset. The team was in distress. Simultaneously, Team Collaboration hit 0.8 — the team was supporting each other through the crisis. This is important context: the problem was systemic, not interpersonal.

- The scope increase was predictable: Sprint 2's incomplete AC and late customer feedback created a specification debt that had to be paid in Sprint 3. The debt collected all at once.

- Fix: The scope freeze protocol (no new work enters an active sprint after kickoff) would have caught this. The developer overload was not due to capacity — it was due to rework on incorrectly specified features.

### Sprint 4 — Recovery (Velocity: 32 SP, Completion: 95%, Avg Sentiment: 0.75)

Sprint 4 is the best sprint in the dataset by every metric. The 0.9 on tooling shows the team's adaptability — they overcame a new PM tool learning curve and still delivered the highest completion rate. The 0.6 on customer feedback shows the feedback loop is improving but not yet at its potential.

- The team proved it can self-correct. Sprint 3's stress did not cascade into Sprint 4 — this is evidence of team resilience that should be explicitly recognized and reinforced.

- The remaining gap: customer feedback sentiment (0.6) is still the lowest category average across both sprints where it appears. The fix is still being implemented. Sprint 5 should see this reach 0.7+.

## 6 Recommendations Ranked by Impact

1. Scope freeze protocol — the single highest-impact change [CRITICAL]

No new work enters an active sprint after kickoff. Any new request goes to the backlog. Exceptions require SM + PO joint agreement and must displace an existing story of equal or greater size. This is not about being rigid — it is about protecting the team from the Sprint 2→3 cascade from recurring. If this one rule had existed in Sprint 2, Sprint 3 would have had normal velocity.

2. QA exploratory testing upskill — Sprint 5 specific urgency [CRITICAL]

ID 203's gap in exploratory testing is the most acute risk for Sprint 5 specifically. AI features (recommendations, chatbot) have non-deterministic outputs. Automated Selenium scripts will cover ~40% of the required validation surface. The remaining 60% requires judgment-driven exploration. Action this sprint, not next quarter: pair ID 203 with a senior tester in Week 1 and have them build a set of 20+ adversarial conversation test scenarios before the mid-sprint demo.

3. Acceptance criteria gate at sprint planning [HIGH]

Stories without complete, agreed AC cannot enter the sprint backlog. The PO owns a checklist with three required elements: measurable acceptance condition, edge case handling specified, and verbal agreement between PO and the implementing developer. This breaks the Sprint 2→3 root cause chain at its source — before the sprint begins rather than mid-sprint after rework has already started.

4. Week 1 customer feedback touchpoint — every sprint [HIGH]

A mid-sprint customer input window (end of Week 1) creates a pivot opportunity before scope is locked. The Sprint 2 pattern showed what happens when feedback arrives at the sprint review — the team gets information they cannot act on. Week 1 is the last point at which a course correction costs days rather than weeks. This should be on the sprint calendar as a non-negotiable event, not an optional stakeholder call.

5. Daily burn rate monitoring by Scrum Master [HIGH]

SM (ID 204) reviews story point burn per team member daily — not just total team velocity. If any member drifts more than 20% from their forecast by day 3, trigger a rebalance conversation the same day. The Sprint 1 workload imbalance and Sprint 3 overload were both visible in burn rate data before they became team-level problems. Catching these at day 3 versus day 8 is the difference between a conversation and a crisis.

6. Push Notifications sequenced after Recommendation Engine [MEDIUM]

This is a product sequencing recommendation, not a process recommendation. Push Notifications sent without personalization data create one of the fastest opt-out patterns in mobile e-commerce. The recommendation engine (Sprint 5) provides the personalization layer that makes notifications worth receiving. Building Push Notifications last in Sprint 6 — after the recommendation API is live — is not a demotion; it is a prerequisite for the feature to work as intended.

04 Team Dynamics & Coaching

## Risk Assessment

The two risks that AI analysis found. Risk 1: ID 202 (Frontend Developer, 4.0/5) appears on two of three Sprint 5 workstreams simultaneously. This creates a single-point-of-failure. If ID 202 encounters a blocker on Workstream A (Recommendations UI integration), Workstream C (Multi-Language) also stalls. SM must monitor ID 202's burn rate daily and have a scope-trade-off decision ready if ID 202 falls behind on either workstream by Day 5. Risk 2: ID 203 (QA Engineer) has an exploratory testing gap that is specifically dangerous for AI features with non-deterministic outputs. This is not a general QA risk — it is acute for Sprint 5. The mitigation must happen in Sprint 5 Week 1, not at the retrospective.

## Full Team Profile Analysis

| ID | Role | Skills | Performance | Hours/Sprint | Skill Gap | Sprint 5 Role | Risk Level |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 201 | Backend Dev | Python · Java · SQL | 4.5/5 | 80h | Cloud computing | Lead WS-A (80%) + WS-B API (20%) | LOW — overallocation risk only |
| 202 | Frontend Dev | JS · React · CSS | 4.0/5 | 85h | Backend integration depth | WS-A UI (50%) + WS-C (50%) | HIGH — 2 workstreams, lowest score |
| 203 | QA Engineer | Selenium · Auto Testing | 4.2/5 | 75h | Exploratory testing | Lead WS-B testing (100%) | HIGH — AI outputs need exploratory testing |
| 204 | Scrum Master | Agile · Conflict Res. | 4.8/5 | 90h | Technical coaching | Cross-workstream coordination | LOW — key risk prevention role |
| 205 | Product Owner | Req Gathering · Stakeholder Management | 4.6/5 | 70h | Competitor analysis tools | WS-C market selection + AC ownership | MEDIUM — copy approval latency risk |
| 206 | UI/UX Designer | Figma · Wireframing · Prototyping | 4.1/5 | 85h | Motion design | WS-C locale UI adjustments (100%) | LOW — motion gap only matters for AR (Sprint 8+) |

## Optimal Team Configurations

### Sprint 5 — Three-Workstream Parallel Configuration

| Workstream | Members | Allocation | Dependency Alert |
| --- | --- | --- | --- |
| A — AI Recommendations (13 SP) | ID 201 + ID 202 | 201: 80% · 202: 50% | API contract finalised by Day 3 (SM enforces) |
| B — AI Chat Support (10 SP) | ID 203 + ID 201 | 203: 100% · 201: 20% | Senior tester pairing for 203 in Week 1 |
| C — Multi-language (9 SP) | ID 202 + ID 206 + ID 205 | 202: 50% · 206: 100% · 205: 30% | PO: market list Day 2, copy approval Day 4 |
| Coordination | ID 204 (Scrum Master) | Cross-workstream | Daily 15-min cross-stream sync; burn monitoring |

Sprint 5 contingency If ID 202 falls behind (2-workstream risk): Workstream C (Multi-Language) is lower-complexity — deprioritize ID 202's contribution to C in Week 2 and focus 202 fully on WS-A. ID 206 continues WS-C independently with PO. If ID 201 becomes unavailable: WS-B (Chat Support) deprioritizes to Sprint 6; WS-A (Recommendations) is the critical path and ID 201 is non-replaceable on the ML model.

### Sprint 6 — Sequential-then-Parallel Configuration

| Sequence | Feature | Week | Members |
| --- | --- | --- | --- |
| Phase 1 (sequential) | Seamless Payment Integration (10 SP) | Week 1 – 1.5 | ID 201 + ID 202: uninterrupted focus, no task-switching |
| Phase 2 (parallel) | Real-Time Order Tracking (8 SP) | Week 1.5 – 2 | ID 201 + partial ID 202 + ID 203 (QA) |
| Phase 2 (parallel) | Voice-Activated Search (9 SP) | Week 1.5 – 2 | ID 202 + ID 206: recommendation engine now live, powering results |
| Phase 3 | Push Notifications (5 SP) | Final days | ID 202 + ID 201: recommendation API integration makes content personalized |

## Simulated Coaching Sessions

These coaching sessions are written as direct, candid conversations — not performance review boilerplate. Each session addresses the team member's specific Sprint 5 risk, not just their general development area.

ID 202 — Frontend Developer

Opening: I want to start with something that might be uncomfortable: you're on two of the three Sprint 5 workstreams, and your performance score of 4.0 is the lowest on the team. I'm not saying that to be harsh — I'm saying it because the gap between where you are and where you need to be in this sprint is real, and you deserve to know it.

Strengths: Your React component work has gotten steadily better sprint over sprint. The UI consistency improvements in Sprint 4 were genuinely ahead of schedule. That discipline is exactly what I need you to apply to the integration work in Sprint 5.

Growth area: The backend integration gap is the immediate threat. When you hit an API question on Workstream A, you need to be at ID 201's desk the same day — not the same week. A 24-hour delay on an API question cascades into a 48-hour delay for the feature. If you're waiting for the stand-up to surface a blocker, you're already a day behind.

Sprint 5 commitments: Sprint 5 commitments: API contract review session with ID 201 on Day 3 (calendar it now). Daily flag to SM if blocked on any integration point for more than 4 hours. If Workstream A falls behind by Day 5, Workstream C is deprioritized — you and SM will make that call together.

ID 203 — QA Engineer

Opening: Workstream B is going to test you. AI chat outputs are non-deterministic — meaning the same input can give a different output on repeat runs. Your Selenium suite cannot fully validate this, and that's not a limitation of your skills — it's a property of the system. The exploratory testing gap matters more in Sprint 5 than it ever has before.

Strengths: Your automation discipline has been one of the most consistent contributions to the team. The regression coverage you built has caught real bugs before production. I want you to bring that same rigor to exploratory testing — it is the same underlying skill applied differently.

Growth area: Here is what I want you to do before the mid-sprint demo: build 20 adversarial conversation scenarios for the chatbot. Not happy-path flows — edge cases. Ambiguous inputs. Questions the model might misinterpret. Questions in unexpected formats. Write them down before you run them. That is exploratory testing: structured hypothesis testing, not random clicking.

Sprint 5 commitments: Sprint 5 commitments: Shadow a senior tester in Week 1 (session booked before Sprint Day 3). Deliver 20 adversarial chat test scenarios before mid-sprint demo. Report non-deterministic failures by scenario ID, not just 'sometimes fails'.

ID 205 — Product Owner

Opening: The feedback cadence improvement you drove in Sprint 4 is the most important process change this team has made in four sprints. It directly broke the Sprint 2→3 failure chain. You should own that — it was your initiative.

Strengths: Your stakeholder management speed is the team's highest-leverage soft skill. You translate vague customer requests into actionable requirements faster than anyone. That's what Sprint 5 needs from you on Multi-Language: fast, precise market selection and copy decisions.

Growth area: The competitor analysis gap has a concrete cost. When you're prioritising the backlog, you're working without market behaviour data — you're relying on stakeholder opinion, which is biased toward existing customers and existing features. Amplitude access gives you actual user behaviour signals from the broader market. Request access this sprint, not next quarter.

Sprint 5 commitments: Sprint 5 commitments: Target market list (first 3 locales) delivered to ID 202 and ID 206 by Day 2 — this is the critical path for Workstream C. All AC for P5 features signed off before sprint kickoff. No story starts without complete AC — if you can't finish it before kickoff, it leaves the sprint.

ID 204 — Scrum Master

Opening: Your 4.8 performance score is the team's highest, and your Sprint 3 de-escalation — keeping the overloaded team from fragmenting — was the most important facilitation work in the project so far. Sprint 5 is a different challenge: three parallel workstreams, two high-risk team members, and AI features that are harder to test than anything this team has built. You need to be in a more active coordination mode than any previous sprint.

Strengths: You caught the Sprint 3 workload crisis before it became a team conflict. That early detection is the exact skill Sprint 5 needs — applied to burn rate monitoring, not team mood.

Growth area: The technical coaching gap matters now because you need to understand the architecture well enough to know when Workstream A is blocking Workstream B and why — before the stand-up. Spend two hours with ID 201 on the recommendation API design before Sprint 5 kicks off. You don't need to write the code; you need to understand the integration points well enough to diagnose a blocker.

Sprint 5 commitments: Sprint 5 commitments: Daily burn rate check per team member (not just total). Explicit blocker escalation protocol: if ID 202 or ID 203 is blocked for more than 4 hours, you intervene that day — not the next stand-up. Day 3 milestone check: all three workstreams confirm their dependencies are resolved.

## Conflict Resolution Strategies

Frontend single-point-of-failure (Sprint 5 — immediate)

ID 202 on 2 workstreams. SM tracks burn daily. Decision rule agreed in advance: if WS-A falls behind by Day 5, ID 202 drops WS-C contribution. No negotiation needed mid-sprint — the rule is pre-agreed.

Scope creep prevention (root cause of Sprint 3 — structural fix)

Scope freeze protocol from Day 1. New work → backlog. SM has explicit authority to reject mid-sprint scope without escalating. Exceptions require SM + PO joint agreement and must displace an equal-size existing story.

QA capacity vs AI feature complexity (Sprint 5 — technical)

ID 203's 75h/sprint is not the constraint — the exploratory testing skill gap is. Pair with senior tester in Week 1. If unavailable externally, SM leads one structured exploratory session using a published heuristic framework (SFDPOT or similar).

PO approval latency risk (Multi-Language — predictable)

Content approval is a historically predictable bottleneck for localisation projects. Pre-agree hard deadlines: market list Day 2, copy Day 4. SM owns escalation if deadlines slip. Partial approval (one locale) unblocks UI work while remaining locales are finalised.

Post-Sprint 3 team psychological safety

Sprint 3 stress may have left residue, particularly for developers who were overloaded. Open Sprint 5 retro with a 'what went well' section before surfacing issues. SM checks in 1:1 with ID 202 and 203 at Week 1 midpoint — not to assess performance, but to ask what they need.