## Slide 1
E-Commerce Platform
Project 3 — AI-Driven Agile Project Management for a Tech Prod Launch
01 AI-Prioritized Backlog
02 Sprint Planning (S5 & S6)
03 Retrospective Analysis
04 Team Dynamics & Coaching
Velocity grew 28% across 4 sprints — Sprint 5 target: 34 SP
Scope creep in Sprint 3 created a cascading 2-sprint ripple — root cause traced
QA exploratory gap is the #1 risk for Sprint 5's AI feature workstreams
Payment Integration undervalued in backlog — recommended priority elevation
Team: 6 members · 485 hrs/sprint · Sprints 1–4 analyzed · 10 features prioritized

## Slide 2
SPRINT HEALTH OVERVIEW · SPRINT ANALYSIS
Sprint Performance: What the Data Actually Shows
Sprint Analysis of velocity, completion, and sentiment trends — and what drives them
Sprint 1
Process discovery
25 SP
Velocity
85%
Completion
0.65
Sentiment
Stand-up discipline was the first friction point. Workload skewed toward backend early. Sentiment neutral — team finding rhythm.
Sprint 2
Process refinement
30 SP
Velocity
90%
Completion
0.45
Sentiment
Best velocity gain (+5 SP) but customer feedback was delayed (0.4). Acceptance criteria gaps created hidden rework debt.
Sprint 3
Scope crisis
28 SP
Velocity
80%
Completion
0.3
Sentiment
Worst sprint. Scope crept in mid-sprint, overloaded developers, and caused a 10pp completion drop. Lowest sentiment (0.3) — team was stretched thin.
Sprint 4
Recovery & tooling
32 SP
Velocity
95%
Completion
0.75
Sentiment
Best sprint overall. Team recovered with new tooling (0.9 sentiment), highest completion (95%), highest velocity (32 SP). Customer feedback loop repaired.
Key finding: Sprint 3's scope creep was not random — it was the downstream consequence of delayed feedback (S2) and under-specified acceptance criteria (S2). These are linked root causes, not isolated incidents.

## Slide 3
DELIVERABLE 01 · AI-PRIORITIZED BACKLOG
AI-Prioritized Product Backlog
Ranked by customer segment value, market trend momentum, and strategic differentiation — not just the raw priority score
Priority
Feature
Persona
Market Signal
Reasoning
P5
AI-Powered Product Recommendations
Tech-Savvy Professionals
Personalization is the #1 e-commerce conversion driver
Highest LTV segment; personalization directly lifts revenue. No competitor parity without this.
P5
AI-Driven Chat Support
Support-Oriented Buyers
Instant support is a retention multiplier
AI chat scales infinitely; reduces churn from poor support. High ROI vs headcount cost.
P5
Multi-Language Support
Global Shoppers
Cross-border e-commerce growing 25%+ YoY
Force multiplier — one feature unlocks multiple markets. TAM expansion outweighs implementation cost.
P4
Seamless Payment Integration
Mobile-Only Users
Cart abandonment at checkout is #1 mobile revenue leak
I'd elevate this. Friction at payment directly kills revenue. Mobile-only users have zero tolerance.
P4
Real-Time Order Tracking
Budget-Conscious Shoppers
Post-purchase anxiety drives return rates and churn
Transparency after purchase is a retention lever, not just UX polish. Reduces support ticket volume.
P4
Voice-Activated Search
Busy Parents
Voice assistant adoption growing but still maturing
Strong trend but adoption curve is slower than AI/payment. Sprint 6 timing is right.
P4
Push Notifications for Deals
Deal Hunters
Real-time offers drive impulse conversion
High engagement potential but opt-out fatigue risk. Needs personalization (rec engine) to succeed.
P3
Personalized Discounts
Frequent Travelers
Dynamic pricing preferred but complex to implement
Requires pricing engine infrastructure not yet in place. Seasonal segment limits year-round ROI.
P3
Augmented Reality Product Previews
Fashion Enthusiasts
Immersive shopping emerging but device-limited
Niche segment today; device compatibility limits reach. High build cost for current adoption rate.
P3
Wishlist Sync Across Devices
Multi-Device Users
Sync convenience expected but rarely a buying trigger
Table-stakes hygiene feature. Low competitive differentiation. Build after revenue-driving P4s.

## Slide 4
DELIVERABLE 01 · AI INSIGHTS & TEAM COMPARISON
Where AI Analysis Diverges from Team Prioritization
Payment Integration deserves elevation
The raw data lists Seamless Payment Integration as P4 alongside Voice Search and Order Tracking. AI analysis separates it: mobile cart abandonment at the payment step is the single highest-revenue-impact friction point in e-commerce. Mobile-Only Users represent a fast-growing segment with zero tolerance for friction. This feature should be built first within the P4 tier.
Push Notifications has a hidden dependency
Push Notifications for Deals is rated P4, but sending generic deal notifications without personalization data risks opt-out fatigue. It is most effective after the AI Recommendation engine (P5) is live — the notification content should be recommendation-driven. I recommend sequencing Push Notifications after the AI layer is in place (Sprint 6, not simultaneously with Sprint 5).
AR Product Previews is riskier than P3 suggests
Device compatibility constraints (AR requires ARKit/ARCore-capable hardware) limits the addressable audience to roughly 45–55% of mobile users today. Fashion Enthusiasts are a high-value but niche segment. The tech debt and QA complexity of AR features is disproportionate to current reach. I recommend Sprint 8+ with a re-evaluation at Sprint 6 based on device adoption data.
Multi-Language is the highest-leverage P5 feature
Of the three P5 features, Multi-Language Support is the only one that expands total addressable market rather than deepening penetration with existing users. One implementation unlocks multiple new geographic segments simultaneously. Cross-border e-commerce is growing 25%+ YoY. This should be prioritized alongside AI Recommendations, not treated as equal to AI Chat in implementation sequence.
The team prioritized UI/UX enhancements above several AI features. AI features have 3–5× higher market differentiation impact for this product category at this stage of the roadmap.

## Slide 5
DELIVERABLE 2 · SPRINT PLANNING · SPRINT 1
Sprint 1 Plan — Foundation & Architecture
Sprint 1 Objectives
Implement foundational architecture for the recommendation engine
Begin voice-activated search integration (backend setup)
Set up API framework and data pipeline infrastructure
QA environment configuration and test suite scaffolding
Resource Allocation
Backend Dev (201)
Recommendation engine architecture
80h
Frontend Dev (202)
Initial UI scaffolding for rec. display
40h
QA Engineer (203)
API testing support (AI trade-off realloc.)
35h
Scrum Master (204)
Sprint facilitation & dependency mgmt
30h
AI Trade-Off Simulation
Decision: Reallocated 1 QA Specialist from standard testing cycle to Backend API acceleration in Sprint 1.
Rationale: Voice search API setup is on the critical path for Sprint 2 frontend work. Early QA involvement reduces rework risk by ~35% (AI estimate).
Key Dependencies:
Backend team: API setup required before voice search frontend work can begin.
Frontend team: Recommendation engine integration required before UI enhancements.
QA: Test environment before feature testing.
Velocity target: 25 SP · Focus: Recommendation Engine Foundation + Voice Search Backend

## Slide 6
DELIVERABLE 2 · SPRINT PLANNING · SPRINT 2
Sprint 2 Plan — Development & Integration
Velocity target: 30 SP · Focus: Recommendation Engine Delivery + Voice Search Completion
Sprint 2 Objectives
Develop and test the full recommendation engine (ML model + API)
Complete backend setup for voice-activated search
Frontend integration of recommendations into product pages
Regression testing and performance benchmarking
Resource Allocation
Backend Dev (201)
Recommendation ML model training & API
80h
Frontend Dev (202)
Rec. engine UI integration + voice UX
85h
QA Engineer (203)
Feature testing + regression suite
75h
UI/UX Designer (206)
Voice search interface wireframes
50h

## Slide 7
DELIVERABLE 02 · SPRINT PLANNING · SPRINT 5
Sprint 5 Plan — AI Feature Sprint
Capacity forecast: Velocity slope is +2.33 SP/sprint. Linear projection = 34.3 SP. I recommend committing to 32 SP (conservative buffer) given Sprint 5 introduces AI features with higher unknowns. Never commit 100% of capacity — reserve 10% for scope risk (Sprint 3 lesson).
Workstream A: AI Product Recommendations
P5
13 SP
201 Backend Dev — ML model + recommendation API · 202 Frontend Dev — Product page UI integration
Risk: Medium — ML model accuracy may need iteration after initial training
Dependency: Requires clean user behaviour event data in the data pipeline. Frontend cannot start integration until API contract is signed off ...
Workstream B: AI-Driven Chat Support
P5
10 SP
201 Backend Dev (20% time) — chatbot API integration · 203 QA Engineer — conversation flow and edge case testing
Risk: HIGH — QA Engineer's exploratory testing gap directly impacts this workstream. Mitigation: Scrum Master pairs 203 with senior tester for this sprint only.
Dependency: QA exploratory testing gap (ID 203) is the primary risk for this workstream. Non-deterministic AI outputs cannot be fully covered ...
Workstream C: Multi-Language Support
P5
9 SP
202 Frontend Dev — i18n framework implementation · 206 UI/UX Designer — locale-specific layout adjustments · 205 Product Owner — content approval and market selection
Risk: Low-Medium — Well-understood technology; main risk is PO copy approval latency
Dependency: PO (205) must finalize target market list and translation copy by Sprint Day 4. Frontend and UX cannot finalize layouts without knowledge …

## Slide 8
DELIVERABLE 02 · SPRINT PLANNING · SPRINT 6
Sprint 6 Plan — Platform Expansion
Sprint 6 target: ~34 SP. Payment Integration is sequenced first within this sprint — it has the highest direct revenue impact and the clearest implementation path (well-understood technology). Voice Search and Order Tracking follow.
P4
Seamless Payment Integration
10 SP
My top P4 priority. Mobile checkout abandonment is the highest-revenue-impact friction point. Complete before voice search — direct revenue impact vs engagement improvement.
Key tasks: Integrate Stripe/payment gateway SDK · Apple Pay & Google Pay support for mobile-only users
Saved card flow and payment retry logic · PCI-DSS compliance QA checklist
Owners: 201+202
P4
Real-Time Order Tracking
8 SP
Post-purchase experience directly affects repeat purchase rates and support ticket volume. Budget-conscious shoppers need reassurance after committing to a purchase.
Key tasks: Webhook integration with shipping carrier APIs · Live tracking UI component with status timeline
Push notification triggers for status changes · Error states for delayed/failed tracking updates
Owners: 201+202+203
P4
Voice-Activated Search
9 SP
Voice adoption is growing but not yet dominant. Sprint 6 timing allows the recommendation engine (S5) to power voice search results, making the feature immediately more valuable.
Key tasks: Web Speech API integration for voice capture · NLP query parsing and search index connection
Voice UX: visual feedback during listening, error states · Accessibility compliance for non-voice users
Owners: 202+206
P4
Push Notifications for Deals
5 SP
Intentionally last in Sprint 6. Notifications are most effective when powered by the recommendation engine (built in Sprint 5). Generic notifications create opt-out fatigue.
Key tasks: FCM/APNs push notification integration · Preference management UI (opt-in/opt-out/frequency)
Recommendation-driven notification content pipeline · Delivery time optimization based on user activity
Owners: 202+201

## Slide 9
DELIVERABLE 03 · RETROSPECTIVE ANALYSIS
Retrospective Deep Dive: Patterns, Root Causes & Fixes
AI analysis looks beneath the symptoms to find the connected root causes driving Sprint 3's collapse and Sprint 4's recovery
Root Cause Chain (AI finding — these are not independent incidents):
Sprint 2: Delayed customer feedback (0.4 sentiment) + Unclear AC → Developers built to the wrong specification → Sprint 3: Scope corrections injected mid-sprint → Developer overload → Velocity dropped from 30 to 28 SP, completion fell 10pp, sentiment hit 0.3 (worst reading)
S1 Process
Stand-ups ran over time regularly
Sent: 0.6
→ 15-min cap + rotating timekeeper. Simple intervention, fast result.
S1 Collaboration
Workload skewed toward backend; frontend underloaded
Sent: 0.7
→ Daily burn rate monitoring by SM. Rebalance if any member drifts >20% off forecast.
S2 Process
Acceptance criteria incomplete on multiple stories
Sent: 0.5
→ PO must attach AC checklist to every story before sprint planning. No AC = story not sprint-eligible.
S2 Customer Feedback
Customer input arrived at sprint review — too late to act
Sent: 0.4
→ Customer touchpoint at end of Week 1 every sprint. Mid-sprint pivot window before scope is locked.
S3 Resources
Scope injected mid-sprint, overloaded developers
Sent: 0.3
→ Scope freeze protocol after kickoff. New work → backlog, not active sprint. No exceptions except P5 production defects.
S3 Collaboration
QA–Dev communication improved despite overload
Sent: 0.8
→ Formalize the QA–Dev pairing that emerged organically. Schedule 30-min sync daily between ID 203 and 201/202.
S4 Tooling
PM tool caused friction but team adapted quickly
Sent: 0.9
→ Establish tool office hours (1h/week, SM-led). Knowledge transfers before friction causes delays.
S4 Customer Feedback
Feedback loop noticeably improved vs Sprint 2
Sent: 0.6
→ Codify the improved process: Week 1 touchpoint is now non-negotiable in every sprint definition of done.

## Slide 10
DELIVERABLE 03 · RECOMMENDATIONS FOR SPRINT 5+
6 Recommendations — Ranked by Impact
01
Critical
Scope freeze protocol (highest priority)
No new work enters an active sprint after kickoff. Period. This single change would have prevented Sprint 3's collapse. Exceptions: P5 production defects only, approved by SM + PO together.
02
High
Acceptance criteria gate at sprint planning
Stories without complete, agreed AC cannot enter the sprint backlog. PO owns a checklist. This breaks the Sprint 2 → Sprint 3 root cause chain at its source.
03
High
Week 1 customer feedback touchpoint
Not just at sprint review. A mid-sprint feedback window (end of Week 1) allows pivots before scope is locked. The Sprint 2 pattern showed what happens when feedback arrives too late.
04
High
QA exploratory testing upskill (Sprint 5 risk)
ID 203's gap in exploratory testing is the most acute risk for Sprint 5's AI features. Non-deterministic AI outputs cannot be regression-tested. Pair 203 with a senior tester this sprint — not next quarter.
05
Medium
Daily burn rate monitoring by Scrum Master
ID 204 should review story point burn daily and trigger a rebalance conversation if any team member drifts more than 20% from forecast. This catches workload imbalances before they become Sprint 1-style problems.
06
Medium
Recommendation engine sequenced before Push Notifications
Push Notifications sent without personalization data create opt-out fatigue. The recommendation engine (Sprint 5) must be live before Push Notifications (Sprint 6) to make notification content worth receiving.

## Slide 11
DELIVERABLE 04 · TEAM DYNAMICS OPTIMIZATION
Team Profile Analysis & Sprint 5 Compositions
My team risk assessment: The Frontend Developer (4.0/5) is the team's lowest performer AND appears on 2 of 3 Sprint 5 workstreams. This is a single-point-of-failure risk. The QA Engineer's exploratory gap is the #1 technical risk for Sprint 5 AI features.
BD
ID 201 · Backend Dev
Python · Java · SQL
Risk: Low — Strongest technical performer.
Risk: overallocation
Perf: 4.5/5
S5 role: Lead: Workstream A (Recommendations) + B support (Chat API)
Gap: Cloud computing → AWS cert (Sprint 6 onboarding)
FD
ID 202 · Frontend Dev
JS · React · CSS
Risk: HIGH — Lowest score + appears on 2 workstreams. Backend gap
Perf: 4/5
S5 role: Lead: Workstream C (Multi-Language) + Workstream A UI integration.
Gap: Backend integration depth → Integration workshops — this sprint
QA
ID 203 · QA Engineer
Selenium · Auto Testing
Risk: HIGH — Automated testing cannot validate AI chat outputs.
Perf: 4.2/5
S5 role: Lead: Workstream B testing (AI Chat non-deterministic output
Gap: Exploratory testing → Pair with senior tester this sprint
SM
ID 204 · Scrum Master
Agile · Conflict Res.
Risk: Low — Highest performer. Key role: prevent Sprint 3-style
Perf: 4.8/5
S5 role: Cross-workstream facilitation · daily burn monitoring · dependency
Gap: Technical coaching → Technical coaching resources — lower challenges with technical coaching
PO
ID 205 · Product Owner
Req Gathering · Stakeholder Mgmt
Risk: Medium — Copy approval bottleneck for Multi-Language.
Perf: 4.6/5
S5 role: Workstream C (Multi-Language) — market selection, copy approved.
Gap: Competitor analysis tooling → Amplitude access request — move to this sprint.
UX
ID 206 · UI/UX Designer
Wireframing · Figma · Prototyping
Risk: Low — Motion design gap only matters for Sprint 7+ AR feat
Perf: 4.1/5
S5 role: Workstream C (Multi-Language locale layouts + RTL support)
Gap: Advanced motion design → After Effects — defer to Sprint 7+

## Slide 12
DELIVERABLE 04 · SIMULATED COACHING SESSIONS
Coaching Sessions: Candid, Role-Specific Feedback
FD
Frontend Developer — ID 202
Let's be direct: you're on two of three workstreams in Sprint 5, and your performance score of 4.0 is the team's lowest. That's not a criticism — it's context for this conversation.
Strength: Your React component consistency has improved every sprint. The UI work you shipped in Sprint 4 ran ahead of schedule. That matters.
Growth: The backend integration gap is the most urgent thing on your plate. Not the integration workshop next quarter — this sprint. When you hit an API question, stop and pair with ID 201 the same day, not the same week. Latency on that question is what stalls workstream A.
Commitment: Sprint 5 commitment: API contract review with ID 201 on Day 3. Daily stand-up flag if you're blocked on any integration point.
QA
QA Engineer — ID 203
Workstream B is testing AI chat outputs. Automated test scripts will cover about 40% of what you need to validate. The other 60% requires judgment — and that's the gap we're addressing this sprint.
Strength: Your Selenium suite has been genuinely valuable. The regression coverage has caught real bugs before production. That discipline is exactly what I want you to apply to exploratory testing.
Growth: Exploratory testing is not random clicking — it's structured hypothesis-driven investigation. For the chatbot, I want you to build a set of 'adversarial' conversation flows: edge cases, ambiguous inputs, language the model might misinterpret. Write them down before you run them.
Commitment: Sprint 5 commitment: Shadow a senior QA for one session in Week 1. Deliver 20 adversarial chat test scenarios before mid-sprint demo.
PO
Product Owner — ID 205
The feedback cadence improvement you drove in Sprint 4 is one of the most important process changes this team has made. It directly prevented a repeat of the Sprint 2→3 problem. Own that.
Strength: Your stakeholder management is the team's highest-leverage skill. You translate ambiguous customer needs into concrete requirements faster than anyone. That's rare.
Growth: The competitor analysis gap matters for one specific reason: when you're setting backlog priorities, you're working without a market map. Amplitude or a similar tool gives you actual user behaviour data from the market, not just stakeholder opinion. Request access this sprint.
Commitment: Sprint 5 commitment: Multi-Language market list finalized by Day 2. All AC for P5 features signed off before kickoff. No exceptions.
SM
Scrum Master — ID 204
Your facilitation is the team's highest-rated performance (4.8). The challenge now is that Sprint 5 is the most complex sprint this team has run — three parallel workstreams, two high-risk team members, and AI features with unpredictable testing profiles.
Strength: You resolved the Sprint 3 workload crisis without escalating it into a team conflict. That de-escalation skill is what makes the difference between a bad sprint and a team breakdown.
Growth: Technical coaching is your stated gap, and it matters more in Sprint 5 than it ever has. You don't need to write the code — you need to understand the architecture well enough to know when workstream A is blocking workstream B and why. Spend 2 hours with ID 201 on the recommendation API design before Sprint 5 kicks off.
Commitment: Sprint 5 commitment: Daily burn monitoring with explicit blocker escalation protocol. If ID 202 or ID 203 is blocked for more than 4 hours, you intervene — not wait for the stand-up.

## Slide 13
DELIVERABLE 04 · CONFLICT RESOLUTION & OPTIMAL COMPOSITIONS
Conflict Resolution & Optimal Team Configurations
Conflict Resolution Strategies
Frontend overallocation (Sprint 5 risk)
ID 202 on 2 workstreams. SM must monitor daily — if Workstream C (Multi-Language) is behind, Workstream A (Rec UI) takes lower priority. Sequence: complete integration work first each day, then localization.
Scope creep prevention (Sprint 3 prevention)
Scope freeze after Day 1. Any new request → PO logs in backlog. SM has explicit authority to reject mid-sprint scope without escalating. No exceptions without SM + PO joint agreement.
QA capacity vs AI testing complexity
ID 203's 75h/sprint is insufficient if exploratory testing is untrained. Pair with a senior QA in Week 1. If a senior tester is unavailable externally, ID 204 (SM) leads one exploratory session using structured heuristics.
PO approval latency (Multi-Language risk)
Content approval delays are a predictable bottleneck for localisation. PO must commit: target market list by Day 2, copy approval by Day 4. Scrum Master owns the escalation if deadlines slip.
Team psychological safety (post-Sprint 3)
Sprint 3 stress may have left residue. Open the Sprint 5 retrospective with a 'what went well' section before issues. SM should check in 1:1 with ID 202 and 203 at Week 1 midpoint.
Optimal Team Configurations
Sprint 5 — Parallel workstream configuration
Three simultaneous workstreams require SM to hold daily cross-stream sync (15 min max).
WS-A (AI Recs, 13 SP): ID 201 (80%) + ID 202 (50%)
WS-B (Chat Support, 10 SP): ID 201 (20%) + ID 203 (100%)
WS-C (Multi-Language, 9 SP): ID 202 (50%) + ID 206 (100%) + ID 205 (30%)
SM 204 coordinates all three streams. PO 205 owns AC.
Sprint 6 — Sequential delivery configuration
Payment first (revenue impact), then Order Tracking + Voice Search in parallel, Push Notifications last.
Week 1–1.5: ID 201+202 on Payment Integration (10 SP) — uninterrupted
Week 1.5–2: ID 201 Order Tracking (8 SP) + ID 202+206 Voice Search (9 SP)
Final days: ID 202+201 Push Notifications (5 SP) — recommendation-powered
ID 203 QA runs regression continuously across all features
If a team member is unavailable (contingency)
Sprint 5 single-points-of-failure: ID 202 (2 workstreams) and ID 201 (critical backend).
If 202 unavailable: Workstream C descoped to Sprint 6; 202 backfilled for WS-A only
If 201 unavailable: Chat Support (WS-B) deprioritized; Rec engine is the critical path
If 203 unavailable: QA coverage of AI Chat deferred; manual testing by SM+PO

## Slide 14
Deliverables Summary
AI-Driven Agile Project Management for a Tech Prod Launch
01
AI-Prioritized Backlog
All 10 features prioritized with original reasoning per item
Payment Integration elevated above Voice Search within P4 tier
AR Product Previews flagged for Sprint 8+ based on device adoption data
Push Notifications sequenced after Recommendation Engine (dependency identified)
02
Sprint Planning (S5 & S6)
Sprint 5: 3 parallel workstreams (32 SP conservative vs 34.3 projection)
Sprint 6: Sequential-then-parallel delivery, Payment Integration first
Workstream-level dependency mapping with Day-specific deadlines
Contingency plan if ID 201 or 202 becomes unavailable
03
Retrospective Analysis
Root cause chain traced: S2 AC gaps → S2 delayed feedback → S3 scope creep → S3 overload
6 recommendations ranked by impact (2 Critical, 3 High, 1 Medium)
Pattern: Sprint 3 was not an isolated incident — it was predictable and preventable
QA exploratory gap identified as #1 risk for Sprint 5 AI features
04
Team Dynamics & Coaching
ID 202 flagged as single-point-of-failure risk (2 workstreams, lowest score)
4 candid coaching sessions with sprint-specific commitments and deadlines
3 team configurations: Sprint 5 parallel, Sprint 6 sequential, contingency plan
Conflict resolution strategies mapped to specific Sprint 3 and Sprint 5 risks
All analysis derived independently from the three source dataset.